## Project Plan
Standard | Task | Notes / Tools
| PHASE 1: Discover (2 months) |  | Status
| Inventory the site | SortSite Professional Microsoft Office Siteimprove Acquia Add sitemap.xml to see basic sitemap WAVE: wave.webaim.org
Document site by pages and content and flag issues
Prioritize pages and content
Decommision content according to records retention
Create safeguards in content creation processes with teammates
| PDFs -- gather all digitally accessibly documents and identify owner, what docs need to be kept, remediated, converted into a webpage, or apply for an exception. See Document remediation tab | https://www.linkedin.com/learning/creating-accessible-pdfs-14445392
Video and audio - gather all videos and identify which need remediation, apply for an exception, or require an alertnative method of delivery of information
PHASE 2: Fixes (2 months)
Fix content issues directly in the site
WCAG 2.1 AA | Headings and labels for positional data, text, links, buttons, etc
WCAG 2.1 AA | Keyboard Navigation
508 | Add Accessibility Statement | https://www.ndit.nd.gov/accessibility-support
WCAG 2.1 AA | Text on all images
WCAG 2.1 AA | Text / Images have contrast ratio 4.5:1 | https://webaim.org/resources/contrastchecker/
Check and fix buttons and links without description labels
Update templates or CMS content blocks
Focus on top-level navigation and homepage
Document (what we did and when)
Training for editors and contributors
Assign PDF updates to the document owners
Content owners begin remediating their documents
| Review Social compliance requirements | Social media needs to be accessible starting on the April 2026 compliance date. Great source I've been following for quite awhile is Accessible Social for some guidance on how to do that - https://www.accessible-social.com/. Compliance also includes mobile and web apps as well, so you may want to start working with NDIT or your vendor on those.
PHASE 3: Content Fixes (3 months)
WCAG 2.1 AA | Captions on all audio and video
Replace and remove documents
Test fixes
Document (what we did and when)
PHASE 4 (2 months)
Final sweep
Retest
Package documentation
Transition into maintenance mode
Ensure training for new hires in onboarding cycle

## Document Remediation
Document | Document Location | Owner | Action | Status | Date of Completion | Notes
|  |  | Select from Dropdown | Select from Dropdown
Section

## Doc Action Definitions
Make a Webpage | Number 1 best practice and recommendation - selecting this action will take the information from within your document and put it on a webpage. This eliminates the need for remediating the document.
Remove | Another great option, if this document is no longer needed on the website. Remember, the website should not be a records management tool.
Archive | The third best option - archived documents are not considered current and do not need remediation. If a accessible version is requested, you must produce one.
Keep | Select this option if your document is current, the info in it is also currently accurate and you need to keep it as a document on the website. The document will require remediation.
Update | Select this option if your document is current, the info in it is NOT currently accurate, but you need to update the info in it and keep it as a document on the website. The document will require remediation.